## Sheet1
|  | Project Name | Aim | Monitoring lead | output / target | Evidence / Indicator | outcome | Evidence / Indicator | Information needed now ~ at scheme outset | HLF output tab | HLF output ref
Programme A: Conserving or restoring the built and natural heritage features that create the historic landscape character
A1: Habitat Stepping Stones
| A1.1 | Bings for Wildlife | To manage two derelict coal bings for biodiversity, especially for invertebrates. | Buglife | 1 ha wildflower meadow enhanced | map, photo | A more interesting and biodiverse landscape with a fit for purpose system in place to ensure benefits are sustained. Where appropriate, the connectivitiy, diversity, and of selected habitats will be mapped. | Before and after fixed point photos, botanical / invertebrate survey, stories from volunteers, Habitat network maps | Photos,have initial baseline botanical / invertebrate surveys for brownfield sites | Biodiversity & Landscape | M36
[5 empty] | up to 1 ha scrub removed | map, photo |  |  |  | Biodiversity & Landscape | K36
[5 empty] | up to 1 ha bare ground created | map, photo |  |  |  | Biodiversity & Landscape | K36
[5 empty] | 10 volunteers participating in management | vol activity record |  |  |  | Volunteers | G7
| A1.2 | Glorious Green Roofs | To create a network of habitat stepping stones in highly developed industrial areas, turning existing flat roofs into green roofs | Buglife | over 200m2 green roof created | map, photo |  |  |  | Biodiversity & Landscape | B120
[5 empty] | 2 large businesses engaged and participating | names and activity notes |  |  |  | Participation & Learning | H14
| A1.3 | An Industrious LNR | To further restore an area which was once the Kinneil Colliery at Bo’ness, into an improved recreational area for people and a haven for wildlife | Falkirk Council | up to 3.6 ha wildflower created | map, photo |  |  |  | Biodiversity & Landscape | M36
[5 empty] | up to 1.57 ha woodland managed | map, photo |  |  |  | Biodiversity & Landscape | K42
[5 empty] | 15 vols learning about site management | vol activity record |  |  |  | Participation & Learning | H&I 12
[5 empty] | 10 volunteers participating | vol activity record |  |  |  | Volunteers | G7
A2: Managing and Restoring Designed Landscapes
| A2.1 | Kinneil Estate Woodlands Reborn | To make significant progress in bringing Kinneil Woods back into sustainable management | Central Scotland Forest Trust | about 14 ha of woodland planted | map, photo | Restored features of historic landscapes, with a fit for purpose system to ensure benefits are maintained, valued and used by local people | Before and after fixed point photos, botanical / invertebrate survey, survey? stories from volunteers and community perceptions | Photos, baseline botanical / invertebrate surveys? Historical research, what was there originally? Anecdotal evidence from local community, what do people think of the landscape now? | Biodiversity & Landscape | K42
| A2.2 | An Orchard at The Pineapple | To reinstate an orchard to an original location at a historical site within a designed landscape, with a mix of modern, productive and local fruit varieties | National Trust for Scotland | 200 fruit trees planted, covering up to 0.8ha | map, photo |  |  |  | Biodiversity & Landscape | K97/L44
[5 empty] | 12 volunteers trained | vol activity record |  |  |  | Volunteers | G7
[5 empty] | 0.5 ha wildflower meadow created | map, photo |  |  |  | Biodiversity & Landscape | M29
[5 empty] | 4 events (120 people) to celebrate fruit trees and nature | counter, numbers attending |  |  |  | Participation & Learning | H31/I31
[5 empty] | 1 traditional shelter built | map, photo |  |  |  | Built Heritage | B43
| A2.3 | Valleyfield Estate Community Orchard | To restore the orchard within the kitchen garden of the former Valleyfield House and Estate held by the Preston family for over 300 years. | West Fife Woodlands | 10 volunteers trained in fruit tree management | vol activity record |  |  |  | Participation & Learning | H&I 12
[5 empty] | 1.2ha land in productive use | map, photo |  |  |  | Biodiversity & Landscape | M44
[5 empty] | 228m of restored hedgerow | map, photo |  |  |  | Biodiversity & Landscape | L87
[5 empty] | 526m new hard paths | map, photo |  |  |  | Access | H14
[5 empty] | 100 fruit trees | map, photo |  |  |  | Biodiversity & Landscape | K97
[5 empty] | Schools and picnic area | map, photo |  |  |  | Participation & Learning | H36
A3: Inner Forth Wetland Network
| A3.1 | Black Devon Wetlands | To restore Black Devon Wetlands in Clackmannanshire, creating a suite of habitats rich in wildlife where local people can engage with the wildlife of the Inner Forth. | RSPB Scotland | 38ha of wet and dry grassland brought into positive management | map, photo | Improved wetland habitats which will attract in particular birds and other species with an ongoing commitment to future management. Where appropriate, the wetlands are going to be accessible and enjoyed by people and the connectivitiy, diversity, and of selected habitats will be mapped. | Photos before and after, bird / botanical / invertebrate survey plus visitor observation and feedback. Habitat network maps. Ariel photography using quad copter | Photos, baseline bird / botanical / invertebrate surveys? Wetland study and phase 1 provides some baseline habitat data, photos at fixed points, initial visitor survey before work commences using standard questionnaire ~ What do people think of the sites now?? | Biodiversity & Landscape | K27
[5 empty] | 2 ha wetland created/enhanced | map, photo |  |  |  | Biodiversity & Landscape | M66
| A3.2 | Bothkennar Pools | To enhance the management of a wetland habitat with established reed beds and a freshwater lagoon. | Falkirk Council | 7.6ha reedbed habitat improved | map, photo |  |  |  | Biodiversity & Landscape | K59
[5 empty] | 500 native trees and shrubs planted | map, photo |  |  |  | Biodiversity & Landscape | K97
[5 empty] | 134m new hawthorn hedge established | map, photo |  |  |  | Biodiversity & Landscape | M87
[5 empty] | 292m stock proof fence erected | map, photo |  |  |  | Biodiversity & Landscape | K96
[5 empty] | 1.2ha woodland managed | map, photo |  |  |  | Biodiversity & Landscape | K42
[5 empty] | 2 tern rafts established | photo |  |  |  | Biodiversity & Landscape | L104
[5 empty] | 460m path made more accessible | map, photo |  |  |  | Access | I14
| A3.3 | Cambus Pools | To restore Cambus Pools SWT Reserve, enhancing its value for people and wildlife. | Scottish Wildlife Trust | 2ha reed bed under improved management | map, photo |  |  |  | Biodiversity & Landscape | K59
[5 empty] | 1 viewing screen constructed | photo |  |  |  | Participation & Learning | H36
[5 empty] | 4 volunteer work days | vol activity record |  |  |  | Participation & Learning | B43
| A3.4 | Kinneil Lagoons ~ Boost the Roost | To enhance a 32ha wetland site on reclaimed land at Kinneil Lagoons to benefit Firth of Forth SPA wintering species and allow visitors an opportunity to connect with the widlifel spectacle of the Inner Forth. | RSPB Scotland | 30ha wetland habitat in positive management | map, photo |  |  |  | Biodiversity & Landscape | K79
[5 empty] | 20ha saline lagoon enhanced | map, photo |  |  |  | Biodiversity & Landscape | K80
[5 empty] | 1 semi-permanent water body created | map, photo
[5 empty] | 2ha woodland removed/thinned | map, photo |  |  |  | Biodiversity & Landscape | K42
[5 empty] | 1 viewing area constructed | photo |  |  |  | Participation & Learning | H36
| A3.5 | Polmaise Lagoons ~ Wetlands | To enhance existing wetland habitats adjacent to the Lower Polmaise Household Waste Recycling Facility, creating a space for wildlife that people can enjoy within an industrial site. | Stirling Council | 2 scrapes created | map, photo |  |  |  | Biodiversity & Landscape | M71
| A3.6 | Skinflats Saline Lagoons | To further enhance the saline lagoon and saltmarsh habitats at RSPB Skinflats Reserve and increase the suitability of the islands and pools for breeding bird species such as ringed plover and common tern. | RSPB Scotland | 3 islands re-profiled and shingle capped | map, photo |  |  |  | Biodiversity & Landscape | K71
[5 empty] | 0.5ha of creek re-profiled | map, photo |  |  |  | Biodiversity & Landscape | L81
[5 empty] | 300m of new creeks created | map, photo |  |  |  | Biodiversity & Landscape | M81
[5 empty] | 0.5ha of scrapes/low points created | map, photo |  |  |  | Biodiversity & Landscape | M71
| A3.7 | Wetter Moss! | To help safeguard the wildlife interest of Wester Moss nature reserve near Fallin, by reducing the rate of water leakage. | Butterfly Conservation | 100m of drain dammed | map, photo |  |  |  | Biodiversity & Landscape | B120
[5 empty] | 1km of informal path created | map, photo |  |  |  | Access | H14
[5 empty] | 0.1ha wetland created | map, photo |  |  |  | Biodiversity & Landscape | K58
[5 empty] | 2 volunteer work parties | vol activity record |  |  |  | Participation & Learning | B43
[5 empty] | 1 event (30 people) | counter, numbers attending |  |  |  | Participation & Learning | H31/I31
[5 empty] | 1 display | photo |  |  |  | Participation & Learning | H33
A4: Woodland Networks and Wildlife Corridors
| A4.1 | Coastal Clacks Woodland Network | To enhance the riparian habitat of the Black Devon and Devon rivers within Coastal Clackmannanshire, bringing woods into active mg'mt bringing the woodland corridors Clackmannan into active management. | Central Scotland Forest Trust | 2.6km of riparian corridor habitat enhanced | map, photo | A more interesting and biodiverse landscape with a fit for purpose system in place to ensure benefits are sustained. Where appropriate there will be increased landowner engagement with a commitment to biodiversity and the connectivitiy, diversity, and of selected habitats will be mapped. | Photos before and after, botanical / invertebrate survey, Habitat network and maps, phone call survey of landowners as part of scheme evaluation | Have photos and baseline surveys, need to identify indicator species | Biodiversity & Landscape | K69
[5 empty] | 10ha woodland brought into mangement | map, photo |  |  |  | Biodiversity & Landscape | K42
[5 empty] | 0.5ha invasive non-native species managed | map, photo |  |  |  | Biodiversity & Landscape | L105
| A4.2 | Falkirk Woodland Network | To increase the quality and quantity of the woodland network within the Falkirk area to create a robust ecological resource. | Central Scotland Forest Trust | 40ha woodland brought into management | map, photo |  |  |  | Biodiversity & Landscape | K32
[5 empty] | 0.5ha invasive non-native species managed | map, photo |  |  |  | Biodiversity & Landscape | L105
| A4.3 | Wildlife Connections | To connect farmers and other land managersthroughout the Inner Forth Landscape with the wildlife that uses their land, and to re- establish wildlife corridors, such as hedgerows, to create a landscape flourishing with biodiversity. | RSPB Scotland | 12 bird surveys | report online |  |  |  | Advice | I11
[5 empty] | 12 managed land conservation audits | report online |  |  |  | Advice | I9
[5 empty] | 1 barn owl nest box scheme in the landscape, size tbc | photos |  |  |  | Biodiversity & Landscape | L106
[5 empty] | 1 tree sparrow nest box scheme in the landscape, size tbc | photos |  |  |  | Biodiversity & Landscape | L107
[5 empty] | 1 land managers' advisory event with at least 10 people | photos |  |  |  | Advice | I8
A5: Safeguarding and Securing Historic Features
| A5.1 | Charlestown Limekilns | To clear vegetation and consolidate Charlestown Limekilns, a key element of a nationally important industrial site in the Inner Forth. | Historic Scotland | Significant south front of limekilns exposed and consolidated | photos | Making historic features safe and accessible, with an ongoing commitment to future management and where appropriate, valued and visited by more people | Before and after photos and survey of users? Expert judgement by archaeologists | Photos of condition of features | Built Heritage | O26
| A5.2 | The View from Clackmannan Tower | To provide increased supervised public access to a nationally important 14th century keep built by Sir Robert Bruce. | Historic Scotland | up to 60 two hour tours over 5 years | bookings diary |  |  |  | Participation & Learning | H34
[5 empty] | up to 1,200 accompanied visits | counter |  |  |  | Participation & Learning | I34
| A5.3 | A Wee Dram at Kennet Pans | To clear vegetation and consolidate Kennetpans, a nationally important industrial site in the Inner Forth, which was the first distillery in the world to be built on an industrial scale. | Historic Scotland | Main building of distillery fully exposed and consolidated | photos |  |  |  | Built Heritage | O26
| A5.4 | Kinneil Estate Church | To create an attractive and educational visitor experience at a historic site, as part of a walk around Kinneil Estate or along the long-distance footpath network, and to safeguard the heritage. | Falkirk Community Trust | 10 people trained in recording inscribed stone | event evaluation |  |  |  | Training & Skills | I23/K23
[5 empty] | 1 published account in Calatria & guide | guide |  |  |  | Access | H37
[5 empty] | Nodal point on footpath trails | photos |  |  |  | Access | I21
[5 empty] | 1 safe and attractive monument | photos |  |  |  | Built Heritage | O35
Programme B: Increasing community participation in local heritage
B1: Conservation Volunteering
| B1.1 | Conservation Volunteering around the Forth | To create a group of volunteers who will be trained in a range of practical natural heritage and survey skills. | RSPB Scotland | 15 volunteers trained in paractical and survey skills | event evaluation | More and different types of people and local groups understand, enjoy, value and take action in the Inner Forth area in ways they did not at the outset. | Evidence from key informants as part of scheme evaluation, volunteer survey and stories |  | Training & Skills | K20
[5 empty] | 15 vols confident to participate in events | event evaluation
B2: Reaching Back, Forth and into the Future
| B2.1 | Cambuskenneth Watergate and Harbour | To investigate the watergate, and establish historical harbour position(s) near Cambuskenneth, to tie the watergate and harbour(s) into its/their historical and gegraphical context | Stirling Council | 300 volunteer person days | vol activity record | Important elements of the built, cultural and natural heritage will be recorded, made publically accessible and celebrated by the local community. People will have gained new skills in researching and understanding heritage. This work will be more accessible in the public domain located on appropariate websites and data records. | Have a standardised evaluation across all the projects. People survey, stories as part of scheme evaluation, access data on NBN website, volunteer survey, include a standardised question, what difference has this (project) made to you? |  | Volunteers | G7
[5 empty] | Volunteers trained in up to 6 skills | event evaluation |  |  |  | Training & Skills | I21/K21
[5 empty] | Historical/archaeological records updated for 2 sites | records available on web-site? |  |  |  | Access | I42
[5 empty] | 4 local schools involved | record bookings and numbers |  |  |  | Participation & Learning | H8
| B2.2 | A Tale of Two Estates | To connect people living around the former Alloa and Clackmannan estates with their fascinating past, and capture more recent memories of Clackmannan Tower, Alloa Tower, Alloa House and the later landscape. | Clackmannanshire Field Studies Society | 75 people trained in research and survey work | event evaluation |  |  |  | Training & Skills | I21/K21
[5 empty] | 50 people trained in archaeological excavation | event evaluation |  |  |  | Training & Skills | I21/K21
[5 empty] | c2.4km of Gartmorn Lade sysyem surveyed | photos, records on web-site? |  |  |  | Industrial Maritime and Transport | L43
[5 empty] | c2.5km of Craigrie Lade system surveyed | photos, records on web-site? |  |  |  | Industrial Maritime and Transport | L43
[5 empty] | Survey Clackmannan & Alloa wagon ways | photos, records on web-site? |  |  |  | Industrial Maritime and Transport | L20
[5 empty] | Survey c6.5km sea walls | photos, records on web-site? |  |  |  | Industrial Maritime and Transport | L32
[5 empty] | Exhibitions, walks and publications from surveys |  |  |  |  | Access | H37
| B2.3 | Forth Crossing | To reconnect communities by engaging groups in research, documentation, knowledge sharing and celebration, surrounding how trading shaped the landscape and culture of the Forth and how the river was a key element in connecting communities. | IFLI team | 1 community mapping resource | map |  |  |  | Access | H41
[5 empty] | 1 social media page | media page on web, followers |  |  |  | Access | H38
[5 empty] | Series of 3 booklets | booklets as pdf online |  |  |  | Access | H37
[5 empty] | 6 local heritage groups trained in desk skills (30 people) | event evaluation |  |  |  | Training & Skills | I24/K24
[5 empty] | 6 local heritage groups trained in mapping (30 people) | event evaluation |  |  |  | Training & Skills | I24/K24
[5 empty] | Pupils from 4 schools trained in mapping | event evaluation |  |  |  | Participation & Learning | H8
[5 empty] | 1 public celebration event with 6 local cttes | counter, photos |  |  |  | Participation & Learning | H32
| B2.4 | The Lost Harbour at Higgins Neuk | To involve local communities in revealing the environmental and cultural history of the Inner Forth landscape through community research, survey and archaeological and environmental investigations of an exemplar site at Higgins Neuk, Airth. | The SCAPE Trust | 30 volunteers trained in excavation and recording | event evaluation |  |  |  | Training & Skills | I21/K21
[5 empty] | 10 volunteers trained in sediment coring | event evaluation |  |  |  | Training & Skills | I21/K21
[5 empty] | More than 150 people engaged | counter, photos
[5 empty] | 2 site open days (60 people) | counter, photos |  |  |  | Participation & Learning | H31/I31
[5 empty] | 2 talks delivered to community | counter, photos |  |  |  | Participation & Learning | H34/I34
[5 empty] | 2 community workshops | event evaluation |  |  |  | Participation & Learning | H24/I24
[5 empty] | Publication of results for variety of audiences | results as pdf available online |  |  |  | Access | I38
| B2.5 | Memories of Mining | To research, remember, share and celebrate memories of mining life among living communities by capturing stories, recollections and images within three ex-mining communities, through working with local heritage groups and local schools. | IFLI team | Create photograph collection via History Pin | collection on History Pin |  |  |  | Access | H41
[5 empty] | 1 Booklet collating results of oral history research | booklet as pdf online |  |  |  | Access | H37
[5 empty] | 3 exhibitions presenting results of oral history | counter, photos |  |  |  | Participation & Learning | H33
[5 empty] | 1 social media page | media page on web |  |  |  | Access | H38
[5 empty] | 20 volunteers paricipating | vol activity record |  |  |  | Participation & Learning | H12/I12
[5 empty] | 6 groups paricipating | record of bookings |  |  |  | Participation & Learning | H12/I12
[5 empty] | 3 schools contributing to oral history research | record of bookings |  |  |  | Participation & Learning | H8
[5 empty] | 1 heritage trail and/or leaflet | information online |  |  |  | Access | H21
| B2.6 | Forth Wildlife Counts | To increase the level of biological recording within the IFLI area and generate as many verified biological records as possible, ensuring that verified records end up in the public domain to aid nature conservation. | IFLI team | 2000 records verified and uploaded onto NBN | counter, screen grab |  |  |  | Access | H42
[5 empty] | 250 participants in 48 training days | counter, photos |  |  |  | Training & Skills | I23/K23
[5 empty] | 50 volunteers regularly submitting biological records | counter |  |  |  | Volunteers | G7
[5 empty] | 50 volunteers trained in usage of i-record or similar | counter, event evaluations |  |  |  | Training & Skills | I23/K23
B3: Outreach and events
| B3.1 | Action for Nature | To raise awareness of, and engage people with, urban and rural biodiversity throughout the Inner Forth area, using ladybirds and orchards as flagship species and habitats. | Central Scotland Forest Trust | 30 primary schools engaged | record of bookings | More and different types of people and local groups understand, enjoy, value and take action the Inner Forth area in ways they did not at the outset. | Evidence from key informants as part of scheme evaluation, include the question, what difference has this (project) made to you? | Need information on numbers of people involved, trained, reached, numbers of sites improved for match funding from SNH | Participation & Learning | H8
[5 empty] | 10 primary schools with habitat creation in grounds | map, photos |  |  |  | Participation & Learning | H38
[5 empty] | 5 heritage fruit varieties re-established | photos |  |  |  | Biodiversity and Landscape | L108
[5 empty] | 3 old orchards restored or re-created | map, photos |  |  |  | Biodiversity and Landscape | L44
[5 empty] | 5 awareness raising activities of training days | counter, photos |  |  |  | Participation & Learning | H25/I25
| B3.2 | Like the Back of My Hand | To promote and raise awareness of the diverse features of natural and cultural heritage around the Inner Forth landscape to residents, visitors and businesses. | IFLI team | 1 IFLI Launch event | flyer, counter, photos |  |  |  | Participation & Learning | H32/I32
[5 empty] | 2 business-focussed events | flyer, counter, photos |  |  |  | Participation & Learning | B43
[5 empty] | 2 community networking events (50 people) | flyer, counter, photos |  |  |  | Participation & Learning | H31/I31
[5 empty] | 26 heritage themed guided walks or workshops | record of bookings |  |  |  | Participation & Learning | H34/I34
[5 empty] | 12 exhibitions, launches or project celerations | flyer, counter, photos |  |  |  | Participation & Learning | H33
[5 empty] | 18 heritage skills taster sessions | sign up list / counter |  |  |  | Participation & Learning | H25/I25
[5 empty] | 8 competitions | record of entries, photos |  |  |  | Participation & Learning | B43
[5 empty] | 3 opportunities to see the landscape in another way | sign up list / counter |  |  |  | Participation & Learning | H34/I34
[5 empty] | 3 volunteer thank you events | flyer, counter, photos |  |  |  | Participation & Learning | H31/I31
Programme C: Increasing access to and learning about the landscape and its heritage
C1: Improving Access
| C1.1 | A Walk to the Wetland | To add value to Black Devon Wetlands by enhancing the adjacent network of paths. | Central Scotland Forest Trust | 1130m of path constructed | map, photos | Increased access infrastructure at key strategic locations enabling people to enjoy the natural and cultural heritage of the area. Increased opportunities for informal recreation that promotes health and well being benefits | Use people counters and surveys at project sites to determine changing patterns of use, possible random sampling by partners. Is it possible to use the website or QR tag surveys linked to the interpretation hubs? | Before and after photos. Need to do baseline surveys with people counters | Access | H14
[5 empty] | 525m of path upgraded | map, photos |  |  |  | Access | I14
[5 empty] | 4 new finger posts and 1 waymarker | photos |  |  |  | Access | H25
[5 empty] | 6 new access gates in deer fence | photos |  |  |  | Access | H25
| C1.2 | Black Devon Wetland Trail | To enable physical access to the wetland site. | RSPB Scotland | 695m path created | map, photos |  |  |  | Access | H14
[5 empty] | 30m boardwalk created | photos |  |  |  | Access | H14
| C1.3 | Cambus Whisky and Wetland Wander | To create an all-abilities circular route to increase access to Forth side heritate in Cambus | Central Scotland Forest Trust | 1350m of path constructed | map, photos |  |  |  | Access | H14
[5 empty] | 5 drop kerbs installed | photos |  |  |  | Access | H25
[5 empty] | Seating at one location | photos |  |  |  | Access | H25
[5 empty] | 6 fingerposts/signs installed | photos |  |  |  | Access | H25
[5 empty] | 3 waymarkers installed | photos |  |  |  | Access | H25
| C1.4 | Clackmannan and Alloa Park Access Improvements | To establish & enhance the Clackmannanshire path network in the River Black Devon area. | Central Scotland Forest Trust | 3 culverts intalled (1 project) | photos |  |  |  | Access | H23
[5 empty] | 1480m of new path created | map, photos |  |  |  | Access | H14
[5 empty] | 50m of fencing installed | photos |  |  |  | Biodiversity & Landscape | K96
[5 empty] | 4 access friendly gates installed | photos |  |  |  | Access | H24
[5 empty] | 6 finger posts installed | photos |  |  |  | Access | H25
[5 empty] | 2 waymarkers installed | photos |  |  |  | Access | H25
| C1.5 | From the Foreshore to Kinneil | To formalise public access between the Kinneil foreshore and the Kinneil Estate. | Falkirk Council | 800m path created between Kinneil Foreshore LNR and Kinneil Estate | map, photos |  |  |  | Access | H14
| C1.6 | Inner Forth Inches Trail | To deliver a looped link between Alloa and Cambus/Tullibody to connect NCN 76 and core paths (22 & 23) | Central Scotland Forest Trust | 915m path improvement | map, photos |  |  |  | Access | H14
[5 empty] | 5 access friendly gates | photos |  |  |  | Access | H24
[5 empty] | 1 people counter | photos |  |  |  | Access | H25
[5 empty] | 10 finger posts | photos |  |  |  | Access | H25
[5 empty] | 2 waymarkers installed | photos |  |  |  | Access | H25
| C1.7 | Kinneil Estate Woodland Wanders | To bring Kinneil Woods back into sustainable management and to deliver recreational amenity and biodiversity benefits | Central Scotland Forest Trust | 2000m of path upgrade | map, photos |  |  |  | Access | H14
[5 empty] | 3 gateways enhanced | photos |  |  |  | Access | I25
| C1.8 | Linking Stirling's Eastern Villages (Fallin and Throsk) | To provide the residents of Fallin and Throsk with a pleasant off-road path linking the villages. | Stirling Council | 1.61km of core path fully signed and waymarked | map, photos |  |  |  | Access | I14
[5 empty] | 215m of improved path surface | map, photos |  |  |  | Part of above
[5 empty] | 580m of vegetation cleared from route | photos |  |  |  | Part of above
| C1.9 | NCN76 ~ The Missing Link at Manor Powis | To provide NCN 76 users with an off-road alternative to the current on-road busy A907 Manor Powis Roundabout and Alloa Road route. | Stirling Council | 950m of off-road cycle path created | map, photos |  |  |  | Access | H11
[5 empty] | Use of 710m of quiet road | photos |  |  |  | Access | I12
[5 empty] | Improved safety for NCN76 users | expert judgement, public comment
[5 empty] | Improved attractiveness of NCN 76? | photos
| C1.10 | Polmaise Lagoons ~ Boardwalk | To provide access to the wetland habitats adjacent to the Lower Polmaise Recycling Facility, creating a space that people can enjoy. | Stirling Council | 700m path created | map, photos |  |  |  | Access | H14
[5 empty] | 31m boardwalk created | photos |  |  |  | Access | H14
[5 empty] | 20 volunteer work days | vol activity record |  |  |  | Participation & Learning | B43
| C1.11 | Views into the Past and Present at Polmont Woods | To facilitate improved public and educational access within Polmont Woods, specifically to improve visibility & access along the Antonine Wall. | Falkirk Council | Felling of mature conifers and removal of timber | photos
[5 empty] | Felling of conifers to form clearance near access path | photos
[5 empty] | Felling of conifers to clear area for outdoor classroom | photos |  |  |  | Participation & Learning | H36
[5 empty] | Clear 30m2 scrub to improve views | photos |  |  |  | Biodiversity & Landscape | K42
[5 empty] | Erect 60m stock-proof fence | photos |  |  |  | Biodiversity & Landscape | K96
[5 empty] | 1 pedestrian gate, 1 field gate | photos |  |  |  | Access | H25
[5 empty] | 81m of 1.8m wide path constructed | photos |  |  |  | Access | H14
[5 empty] | Sow 60m of 1.8m wide grass path | photos |  |  |  | Part of above
C2: Active Communities
| C2.1 | An Active Landscape | To deliver a variety of outdoor activities which will enable communities to get active and explore the many natural and built heritage facets of the landscape. | IFLI Natural Heritage and Volunteer Officer | 7 trained photo trails surveyors (1 event) | event evaluation | More and different types of people and local groups understand, enjoy, value and take action the Inner Forth area in ways they did not at the outset. | Evidence from key infomants (eg walks leaders) as part of the scheme evaluation |  | Participation & Learning | H25/I25
[5 empty] | 8 trained walks leaders (1 event) | event evaluation |  |  |  | Participation & Learning | H25/I25
[5 empty] | 4 trained assistant cycle leaders (1 event) | event evaluation |  |  |  | Participation & Learning | H25/I25
[5 empty] | 18 routes on Fieldfare Trust's phototrails site | event evaluation |  |  |  | Access | H21
[5 empty] | Creation of 1 Trail Route map (500 copies) | website screen grab |  |  |  | Access | H36
[5 empty] | 210 paricipants of walks or cycles | counter |  |  |  | Access | H27/I27
[5 empty] | 40 led walks or cycles | flyers, record of bookings |  |  |  | Access | H27/I27
[5 empty] | 5 groups involved in mapping IFLI Trail routes (25 people) | counter, photos |  |  |  | Participation & Learning | H12/I12
[5 empty] | 6 Sustrans Active Travel Champions (1 course) | photos |  |  |  | Training & Skills | I23/K23
[5 empty] | 15 volunteers maintaining trail routes | vol activity record |  |  |  | Volunteers | G7
[5 empty] | 1 geo-caching trail created | trail as pdf online |  |  |  | Access | H21
C3: Telling the Inner Forth Story
| C3.1 | Telling the Inner Forth Story | To provide a landscape-wide suite of engaging and effective interpretation, which interpret the natural, historical and cultural heritage of the landscape and increase understanding and appreciation of its value. | IFLI Communications and Interpretation Officer | 1 creative arts outreach project (40 people) | photos available online | Increased awareness and understanding amongst all individuals and groups of what makes the Inner Forth special and the threats to the unique heritage. | Stories of activities and increased awareness of the natural and cultural heritage | Use the initial audit of interpretation already in place to map change | Participation & Learning | H28/I28
[5 empty] | 1 series of interpretive hubs | photos |  |  |  | Access | H34
[5 empty] | 1 series of interpretive markers | photos |  |  |  | Access | H34
[5 empty] | 1 pop up travelling exhibition | counter, photos |  |  |  | Access | H34
[5 empty] | 2 interpretive bird screeens | photos |  |  |  | Access | H34
[5 empty] | 1 mobile application | app downloads |  |  |  | Access | H40
[5 empty] | 1 Inner Forth Leaflet | leaflet as pdf online |  |  |  | Access | H36
[5 empty] | Inner Forth Website updated | google analytics |  |  |  | Access | I38
C4: A learning Landscape
| C4.1 | Future Tides | To engage school children with the changing landscape and wildlife of the Inner Forth to build a greater understanding of why the landscape is shaped like it is and how it may change in the future. | RSPB Scotland | 3 schools taking part in landscape project | activity record | Increased awareness and understanding amongst all individuals and groups of what makes the Inner Forth special and the threats to the unique heritage. | Stories of activities and increased awareness of the natural and cultural heritage | Pre visit form for visits to guage awareness and knowledge | Participation & Learning | H8
[5 empty] | 12 class visits on site (300 people) | record of bookings |  |  |  | Participation & Learning | H21/I21
[5 empty] | 1 debate event (80 people) | photos, outcomes report |  |  |  | Participation & Learning | H31/I31
| C4.2 | Polmaise Lagoons ~ Education Facilities | To provide a centre for environmental education based around the recycling facility and natural environment. | Stirling Council | 4 schools visits, ambition?? | counter, photos |  |  |  | Participation & Learning | H21/I21
[5 empty] | 1 study station installed | photos |  |  |  | Access | H33
[5 empty] | 1 classroom facility | photos, activity record |  |  |  | Built Heritage | Q29
Programme D: Increasing training opportunities in local heritage
D1: Developing Our Skills
| D1.1 | Blair Castle Heritage Skills | To provide a range of heritage skills training opportunities to improve management of and increase access to the Blair Castle estate. | Link Group Ltd | Up to 30 people trained in land based heritage skills | event evaluation | Participants have increased their skills and are motivated to find work in the heritage / land based sectors. There is an increase in the number of people gaining employment in the environmental, heritage and landbased sector | Stories from participants about employment gained from training. Include a standardised question, what difference has this (training) made to you? |  | Training and Skills | I21/K21
[5 empty] | 6 Heritage skills events (60 people) | record of bookings |  |  |  | Participation & Learning | H31/I31
[5 empty] | 3 Edible border sites established | photos |  |  |  | Biodiversity & Landscape | B120
| D1.2 | Landscape Management Apprenticeships | Provide opportunities to gain Employability Awards and Vocational Skills Qualifications through on-site training and work experience. | Falkirk Council | 30 unemployed people gain Falkirk Employability Award | record of awards |  |  |  | Training and Skills | C82
[5 empty] | 30 unemployed people gain Vocational Skills Quals. | record of qualifications |  |  |  | Training and Skills | C83
| D1.3 | Drystone Dyke Apprenticeships | To provide traditional skills training through a LANTRA dry stone wall apprenticeship based at the Kinneil Estate. | Falkirk Council | 100m of drystone wall created | photos |  |  |  | Biodiversity & Landscape | K95
[5 empty] | 8 clients gaining LANTRA Drystone wall apprenticeship | record of awards |  |  |  | Training and Skills | C84
[5 empty] | 8 clients gaining Falkirk Employability award | record of awards |  |  |  | Training and Skills | C82
| D1.4 | Training Tomorrow's Talent | To create paid employment training opportunities for unemployed people from the IFLI area, in the heritage/environmental sector. | Clacks Council IFLI Team | 11 employment and training opportunities created ~ yr1 | training evaluation, records |  |  |  | Training and Skills | K38
[5 empty] | 4 employment / training opportunities created ~ yrs 2 - 4 | training evaluation, records |  |  |  | Training and Skills | K38
[5 empty] | 6 research bursaries per year for students | research output per student |  |  |  | Participation & Learning | I10
| D1.5 | Conservation Masonry Skills | To up-skill trades people working on traditional buildings in the IFLI area through masonry conservation and consolidation techniques | Historic Scotland | 10 people gaining NPA Conservation of Masonry | training evaluation, record of awards, employment records | People are better at working on traditional buildings, with higher quality bids for work on heritage buildings | Stories from participants, and key informants. What difference has this training made to you? |  | Training and Skills | C85
| D1.6 | Researching our Local Heritage | To provide support and training to community groups to enable them to successfully participate in and run projects to research, record, showcase and preserve elements of local heritage. | IFLI team | 14 training workshops held (15 people) | record of bookings | Important elements of the built, cultural & natural heritage will be recorded and celebrated. People will gain new skills in researching and understanding heritage. | Stories from participants. Not just skills gained but in other areas of life. What difference has this training made to you? |  | Training and Skills | I24/K24
[5 empty] | 30 individuals participating and supported | photos, activity record |  |  |  | Participation & Learning | I12
[5 empty] | 5 community groups supported to participate in projects (30 people above) | photos, activity record |  |  |  | Participation & Learning | H12
There is an increase in the number of people gaining employment in the environmental, heritage and landbased sector